## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
Link Git : https://github.com/nhatlq20/SWP391
FunctionName | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration | Time: Begin | Time: Deadline | Time: Resit | Note
View Medicine List | Guest Medicine View | Simple | Iteration 1 | CE191071 | Đỗ Nguyên Hạo | Iteration 1 | 2026-02-01 | 2026-02-03 | 2026-02-04 | Done
View Medicine Detail | Guest Medicine View | Simple | Iteration 1 | CE191071 | Đỗ Nguyên Hạo | Iteration 1 | 2026-02-01 | 2026-02-03 | 2026-02-04 | Done
Search Medicine | Guest Medicine View | Complex | Iteration 1 | CE191071 | Đỗ Nguyên Hạo | Iteration 1 | 2026-02-05 | 2026-02-06 | 2026-02-07 | Done
View Medicine List For DashBoard | Medicine Management | Simple | Iteration 1 | CE191071 | Đỗ Nguyên Hạo | Iteration 1 | 2026-02-08 | 2026-02-09 | 2026-02-10 | Done
Create Medicine | Medicine Management | Complex | Iteration 1 | CE191071 | Đỗ Nguyên Hạo | Iteration 1 | 2026-02-09 | 2026-02-11 | 2026-02-12 | Done
Update Medicine | Medicine Management | Complex | Iteration 1 | CE191071 | Đỗ Nguyên Hạo | Iteration 1 | 2026-02-09 | 2026-02-11 | 2026-02-12 | Done
Delete Medicine | Medicine Management | Simple | Iteration 1 | CE191071 | Đỗ Nguyên Hạo | Iteration 1 | 13/2/2026 | 2026-02-14 | 2026-02-15 | Done
Chat With AI Agent | AI Assistant | Complex | Iteration 3 | CE191071 | Đỗ Nguyên Hạo | Iteration 3 | 2026-05-03 | 2026-03-07 | 2026-03-08 | Done
Add Medicine To Cart | Cart Management | Medium | Iteration 2 | CE190875 | Lê Quang Nhật | Iteration 2 | 2026-02-02 | 2026-02-04 | 2026-02-05 | Done
Update Medicine From Cart | Cart Management | Medium | Iteration 2 | CE190875 | Lê Quang Nhật | Iteration 2 | 2026-02-06 | 2026-02-07 | 2026-02-08 | Done
Delete Medicine From Cart | Cart Management | Simple | Iteration 2 | CE190875 | Lê Quang Nhật | Iteration 2 | 2026-02-06 | 2026-02-07 | 2026-02-08 | Done
Create Order | Order Management | Complex | Iteration 2 | CE190875 | Lê Quang Nhật | Iteration 2 | 2026-02-09 | 2026-02-11 | 2026-02-12 | Done
View Order Detail | Order Management | Medium | Iteration 2 | CE190875 | Lê Quang Nhật | Iteration 2 | 2026-02-13 | 2026-02-14 | 2026-02-15 | Done
View Orders List | Order Management | Simple | Iteration 2 | CE190875 | Lê Quang Nhật | Iteration 2 | 2026-02-13 | 2026-02-14 | 2026-02-15 | Done
View Orders List For DashBoard | Order Management For DashBoard | Simple | Iteration 2 | CE190875 | Lê Quang Nhật | Iteration 2 | 2026-02-16 | 2026-02-19 | 2026-02-20 | Done
View Order Detail For DashBoard | Order Management For DashBoard | Simple | Iteration 2 | CE190875 | Lê Quang Nhật | Iteration 2 | 2026-02-16 | 2026-02-19 | 2026-02-20 | Done
Set Order Status | Order Management For DashBoard | Medium | Iteration 2 | CE190875 | Lê Quang Nhật | Iteration 2 | 2026-02-16 | 2026-02-19 | 2026-02-20 | Done
Delete Order For DashBoard | Order Management For DashBoard | Simple | Iteration 2 | CE190875 | Lê Quang Nhật | Iteration 2 | 2026-02-16 | 2026-02-19 | 2026-02-20 | Done
View Customers List | Customer Management | Simple | Iteration 2 | CE190875 | Lê Quang Nhật | Iteration 2 | 2026-02-21 | 2026-02-22 | 2026-02-23 | Done
View Customer Detail | Customer Management | Simple | Iteration 2 | CE190875 | Lê Quang Nhật | Iteration 2 | 2026-02-21 | 2026-02-22 | 2026-02-23 | Done
View Import List | Import Management | Medium | Iteration 2 | CE190885 | Phan Nhật Cường | Iteration 2 | 2026-02-13 | 14/2/2026 | 15/2/2026 | Done
Create Import | Import Management | Complex | Iteration 2 | CE190885 | Phan Nhật Cường | Iteration 2 | 16/2/2026 | 18/2/2026 | 19/2/2026 | Done
Set Import Status | Import Management | Complex | Iteration 2 | CE190885 | Phan Nhật Cường | Iteration 2 | 20/2/2026 | 21/2/2026 | 22/2/2026 | Done
View Import Detail | Import Management | Medium | Iteration 2 | CE190885 | Phan Nhật Cường | Iteration 2 | 20/2/2026 | 21/2/2026 | 22/2/2026 | Done
Update import | Import Management | Complex | Iteration 2 | CE190885 | Phan Nhật Cường | Iteration 2 | 23/2/2026 | 24/2/2026 | 25/2/2026 | Done
Delete import | Import Management | Complex | Iteration 2 | CE190885 | Phan Nhật Cường | Iteration 2 | 23/2/2026 | 24/2/2026 | 25/2/2026 | Done
View Revenue | Revenue Management | Complex | Iteration 3 | CE190885 | Phan Nhật Cường | Iteration 3 | 28/2/2026 | 2026-03-01 | 2026-03-02 | Done
View Category List | Category Management | Simple | Iteration 1 | CE190462 | Trịnh Trung Kiên | Iteration 1 | 2026-02-03 | 2026-02-05 | 2026-02-06 | Done
View Category Detail | Category Management | Medium | Iteration 1 | CE190462 | Trịnh Trung Kiên | Iteration 1 | 2026-02-03 | 2026-02-05 | 2026-02-06 | Done
Create Category | Category Management | Simple | Iteration 1 | CE190462 | Trịnh Trung Kiên | Iteration 1 | 2026-02-07 | 2026-02-08 | 2026-02-09 | Done
Delete Category | Category Management | Simple | Iteration 1 | CE190462 | Trịnh Trung Kiên | Iteration 1 | 2026-02-07 | 2026-02-08 | 2026-02-09 | Done
View Review | Review Management | Simple | Iteration 2 | CE190462 | Trịnh Trung Kiên | Iteration 2 | 2026-02-14 | 2026-02-15 | 2026-02-16 | Done
Write Review | Review Management | Medium | Iteration 2 | CE190462 | Trịnh Trung Kiên | Iteration 2 | 2026-02-17 | 2026-02-18 | 2026-02-19 | Done
View Owner Reviews | Review Management | Medium | Iteration 2 | CE190462 | Trịnh Trung Kiên | Iteration 2 | 2026-02-20 | 2026-02-22 | 2026-02-23 | Done
Delete Owner Review | Review Management | Simple | Iteration 2 | CE190462 | Trịnh Trung Kiên | Iteration 2 | 2026-02-20 | 2026-02-22 | 2026-02-23 | Done
Delete Review For DashBoard | Review Management For Dashboard | Medium | Iteration 3 | CE190462 | Trịnh Trung Kiên | Iteration 3 | 2026-02-24 | 2026-02-26 | 2026-02-27 | Done
Write Review For DashBoard | Review Management For Dashboard | Simple | Iteration 3 | CE190462 | Trịnh Trung Kiên | Iteration 3 | 2026-02-24 | 2026-02-26 | 2026-02-27 | Done
View All Reviews | Review Management For Dashboard | Simple | Iteration 3 | CE190462 | Trịnh Trung Kiên | Iteration 3 | 2026-02-24 | 2026-02-26 | 2026-02-27 | Done
Login | Authentication | Complex | Iteration 1 | CE190367 | Lê Trường An | Iteration 1 | 28/2/2026 | 2026-03-01 | 2026-03-02 | Done
Register | Authentication | Complex | Iteration 1 | CE190367 | Lê Trường An | Iteration 1 | 2026-03-03 | 2026-03-04 | 2026-03-05 | Done
Logout | Authentication | Simple | Iteration 1 | CE190367 | Lê Trường An | Iteration 1 | 2026-03-03 | 2026-03-04 | 2026-03-05 | Done
View Staff List | Staff Management | Simple | Iteration 2 | CE190367 | Lê Trường An | Iteration 2 | 2026-02-14 | 2026-02-15 | 2026-02-16 | Done
View Staff Detail | StaffManagement | Simple | Iteration 3 | CE190367 | Lê Trường An | Iteration 3 | 2026-02-14 | 2026-02-15 | 2026-02-16 | Done
Create Staff | Staff Management | Medium | Iteration 2 | CE190367 | Lê Trường An | Iteration 2 | 2026-02-17 | 2026-02-18 | 2026-02-19 | Done
Delete Staff | Staff Management | Simple | Iteration 2 | CE190367 | Lê Trường An | Iteration 2 | 2026-02-17 | 2026-02-18 | 2026-02-19 | Done
Update Profile | Profile Management | Simple | Iteration 2 | CE190367 | Lê Trường An | Iteration 2 | 2026-02-07 | 2026-02-09 | 2026-02-10 | Done
Change Password | Profile Management | Medium | Iteration 1 | CE190367 | Lê Trường An | Iteration 1 | 2026-02-07 | 2026-02-09 | 2026-02-10 | Done
View Voucher List | Voucher Management | Simple | Iteration 3 | CE190875 | Lê Quang Nhật | Iteration 3 | 2026-03-06 | 2026-03-07 | 2026-03-08 | Done
Create Voucher | Voucher Management | Complex | Iteration 3 | CE190875 | Lê Quang Nhật | Iteration 3 | 2026-03-09 | 2026-03-11 | 2026-03-12 | Done
Update Voucher | Voucher Management | Medium | Iteration 3 | CE190875 | Lê Quang Nhật | Iteration 3 | 2026-03-12 | 2026-03-11 | 2026-03-12 | Done
Delete Voucher | Voucher Management | Simple | Iteration 3 | CE190875 | Lê Quang Nhật | Iteration 3 | 2026-03-13 | 2026-03-14 | 2026-03-15 | Done
View Voucher Detail | Voucher Management | Simple | Iteration 3 | CE190875 | Lê Quang Nhật | Iteration 3 | 2026-03-15 | 2026-03-14 | 2026-03-15 | Done
In-charge Full Name | In-charge Roll Number | Contributions
Phan Nhật Cường | CE190885 | 20.3%
Lê Quang Nhật | CE190875 | 21.2%
Đỗ Nguyên Hạo | CE191071 | 20.7%
Lê Trường An | CE190367 | 19.7%
Trịnh Trung Kiên | CE190462 | 18.1%